## Estimate
|  |  | Estimate hours [h] | [14 empty] | Dozent INF | Senior Researcher INF | Researcher INF | Dozent EMS | Senior Researcher EMS | Researcher EMS | Technician | Manufacturing
WP Nr. | WP / Tasks | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 |  | Estimate [%] | 5% | 8% | 20% | 5% | 12% | 30% | 7% | 12.5% | 99.5%
[17 empty] | costs [CHF/h] | 165 | 125 | 105 | 165 | 125 | 105 | 85 | 85
[17 empty] | mean costs [CHF/h] | 8.25 | 10 | 21 | 8.25 | 15 | 31.5 | 5.95 | 10.625 | 110.575
1 | Requirements engineering / Concept | 200 | 80 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
| Requirements engineering | 60 | 2016-11-01: 30; 2016-12-01: 30
| Concept development | 40 | 2016-11-01: 20; 2016-12-01: 20
| Sensor concept global and local | 40 | 2016-11-01: 20; 2016-12-01: 20
| Sensor concept, sensor fusion, data flow | 15 | 2016-12-01: 15
| Recharging management | 15 | 2016-12-01: 15
| Power Management, Battery, Current distribution | 20 | 2016-12-01: 20
| Chair digitizing | 10 | 2016-11-01: 10
2 | Active caster module | 600 | 95 | 140 | 235 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600
| Drive concept, local power electronics | 50 | 2016-11-01: 30; 2016-12-01: 20
| Sensor concept | 60 | 2016-11-01: 20; 2016-12-01: 40
| Construction and development | 200 | 2016-11-01: 40; 2016-12-01: 80; 2017-01-01: 80
| Order of power electronics | 5 | 2016-11-01: 5
| Order, Production and montage | 75 | 2017-01-01: 75
| Integration, motor tests (with other drives) | 40 | 2017-01-01: 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 40 | 2017-01-01: 40
| Installation and commissioning the right drives and Construction | 130 | 2017-02-01: 130
3 | Algorithms and controllers | 125 | 35 | 75 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125
| Transformation algorithms | 55 | 2016-11-01: 10; 2016-12-01: 30; 2017-01-01: 15
| Exploration / development of a generic dynamic model | 30 | 2016-11-01: 10; 2016-12-01: 20
| Algorithms for cartesian controllers | 30 | 2016-11-01: 15; 2016-12-01: 15
| Verification / Experiments | 10 | 2016-12-01: 10
4 | First test only with baseframe | 250 | 0 | 0 | 140 | 85 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 300 | 250
| Construction and development the Baseframe | 150 | 2017-01-01: 140; 2017-02-01: 10
| Order and Production | 10 | 2017-02-01: 10
| Mounting the drives | 40 | 2017-02-01: 40
| Commissioning and testing (not with the right electronics) | 50 | 2017-02-01: 25; 2017-03-01: 25
5 | Robot software development | 750 | 0 | 0 | 120 | 155 | 150 | 150 | 150 | 25 | 0 | 0 | 0 | 0 | 0 | 700
| Control-System for the drives | 150 | 2017-01-01: 120; 2017-02-01: 30
| Sensors commissioning | 50 | 2017-02-01: 50
| People detection | 150 | 2017-02-01: 75; 2017-03-01: 75
| Navigation, position detection, obstacle detection, | 150 | 2017-03-01: 75; 2017-04-01: 75
| Control-System with sensors | 100 | 2017-04-01: 75; 2017-05-01: 25
| Safety-System | 50 | 2017-05-01: 50
| Sequencer | 100 | 2017-05-01: 75; 2017-06-01: 25
6 | Constructive postprocessing of the Chair | 300 | 0 | 0 | 30 | 150 | 30 | 50 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 300
| Construction and manufacture of the prototype | 200 | 2017-01-01: 30; 2017-02-01: 150; 2017-03-01: 20
| Order and Production | 10 | 2017-03-01: 10
| Assembly and integration Automation module | 50 | 2017-04-01: 50
| Commissioning and testing | 40 | 2017-05-01: 40
7 | Small series production mechanik | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 45 | 55 | 0 | 0 | 0 | 0 | 60 | 110
| Order and produce of all mechanical parts | 10 | 2017-05-01: 10
| Montage | 45 | 2017-06-01: 45
| Commissioning and testing | 55 | 2017-07-01: 55
8 | Control hardware | 400 | 40 | 60 | 65 | 45 | 45 | 40 | 60 | 45 | 0 | 0 | 0 | 0 | 0 | 400
| Main control: Evaluation, Procurement, Testing | 20 | 2017-01-01: 20
| EtherCAT | 100 | 2016-11-01: 40; 2016-12-01: 60
| Servo Drives: Evaluation, Procurement, Testing | 15 | 2017-01-01: 15
| Sensor concept global and local | 90 | 2017-01-01: 30; 2017-02-01: 30; 2017-03-01: 30
| Security electronics: Evaluation, Procurement, Testing | 30 | 2017-02-01: 15; 2017-03-01: 15
| PCBs and communication module development | 80 | 2017-04-01: 40; 2017-05-01: 40
| Order and Production for Prototype | 50 | 2017-05-01: 20; 2017-06-01: 30
| Hardware tests | 15 | 2017-06-01: 15
9 | Basic software development | 700 | 80 | 100 | 140 | 70 | 80 | 50 | 110 | 70 | 0 | 0 | 0 | 0 | 0 | 700
| Robotics Library development, control system & safety system | 150 | 2016-11-01: 40; 2016-12-01: 50; 2017-01-01: 60
| Robotics Library development, sequencer | 70 | 2017-01-01: 10; 2017-02-01: 40; 2017-03-01: 20
| Robotics Library development, hardware abstraction layer | 120 | 2016-12-01: 10; 2017-01-01: 30; 2017-02-01: 30; 2017-03-01: 50
| Test Cases | 100 | 2017-05-01: 50; 2017-06-01: 50
| Operating system support (Kernel, QNX, …) | 120 | 2016-11-01: 40; 2016-12-01: 40; 2017-01-01: 40
| ROS interfaceing | 100 | 2017-03-01: 10; 2017-04-01: 50; 2017-05-01: 40
| Global Data Flow | 40 | 2017-05-01: 20; 2017-06-01: 20
10 | Small series production electronic | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 70 | 40 | 0 | 0 | 150
| Extensive testing | 40 | 2017-07-01: 40
| Rework of the PCBs | 40 | 2017-08-01: 40
| Order and produce of all electronic parts | 30 | 2017-08-01: 30
| Hardware tests | 40 | 2017-09-01: 40
11 | Art performance development | 250 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 230 | 0 | 0 | 0 | 250
| Concept development | 20 | 2017-04-01: 20
| Algorithms for demonstration | 150 | 2017-08-01: 150
| Simulation of the performance | 80 | 2017-08-01: 80
12 | Usability test, optimization | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 42
| Usability test, optimization, demonstration, exception tests | 42 | 2017-09-01: 42
13 | Project Management | 360 | 40 | 40 | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20 | 80
| Reporting, controlling and documetation | 360 | 40 | 40 | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 20 | 20 | 20 | 20
| Total [h]: | 4237 | 370 | 535 | 775 | 665 | 360 | 340 | 400 | 215 | 115 | 320 | 102 | 20 | 20
| CHF/h | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575 | 110.575
| Total [CHF] | 468506.275 | 40912.75 | 59157.625 | 85695.625 | 73532.375 | 39807 | 37595.5 | 44230 | 23773.625 | 12716.125 | 35384 | 11278.65 | 2211.5 | 2211.5

## Total_Actual
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 139.75 | 200 | 125.75 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 40 | 60 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 55.75 | 40 | 55.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sensor concept global and local | 33 | 40 | 25 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sensor concept, sensor fusion, data flow | 2 | 15 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Recharging management | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Power Management, Battery, Current distribution | 4 | 20 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Chair digitizing | 5 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active caster module | 78 | 600 | 40 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 20 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sensor concept | 48 | 60 | 10 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development | 10 | 200 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order of power electronics | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order, Production and montage | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration, motor tests (with other drives) | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Installation and commissioning the right drives and Construction | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Algorithms and controllers | 24.5 | 125 | 19.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 19.5 | 55 | 19.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Exploration / development of a generic dynamic model | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Algorithms for cartesian controllers | 5 | 30 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Verification / Experiments | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and Production | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mounting the drives | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Commissioning and testing (not with the right electronics) | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sensors commissioning | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| People detection | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Navigation, position detection, obstacle detection, | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System with sensors | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Safety-System | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sequencer | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and Production | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Assembly and integration Automation module | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Commissioning and testing | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Montage | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Commissioning and testing | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Control hardware | 53 | 400 | 15 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EtherCAT | 53 | 100 | 15 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sensor concept global and local | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Security electronics: Evaluation, Procurement, Testing | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PCBs and communication module development | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and Production for Prototype | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hardware tests | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Basic software development | 69 | 700 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 25 | 150 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, sequencer | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, hardware abstraction layer | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test Cases | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Operating system support (Kernel, QNX, …) | 44 | 120 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ROS interfaceing | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Global Data Flow | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Rework of the PCBs | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all electronic parts | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Hardware tests | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Algorithms for demonstration | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Simulation of the performance | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Project Management | 65.05 | 360 | 32.05 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 65.05 | 360 | 32.05 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total [h]: | 429.3 | 4237 | 301.3 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h |  | 110.575 | 134.0441 | 116.875 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Total [CHF] | 0 | 468506.275 | 40387.5 | 14960 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## GUTC
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 0 | 60
| Concept development | 0 | 40
| Sensor concept global and local | 0 | 40
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 0 | 60
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 0 | 4237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 105 | 110.575 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Total [CHF] | 0 | 468506.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## STER
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 5 | 200 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 0 | 60
| Concept development | 0 | 40
| Sensor concept global and local | 0 | 40
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 5 | 10 | 2016-11-01: 5
2 | Active caster module | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 0 | 60
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 5 | 4237 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 85 | 110.575 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85
| Total [CHF] | 425 | 468506.275 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## LANS
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 49 | 200 | 35 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 20 | 60 | 2016-11-01: 20
| Concept development | 5 | 40 | 2016-11-01: 5
| Sensor concept global and local | 13 | 40 | 2016-11-01: 5; 2016-12-01: 8
| Sensor concept, sensor fusion, data flow | 2 | 15 | 2016-12-01: 2
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 4 | 20 | 2016-12-01: 4
| Chair digitizing | 5 | 10 | 2016-11-01: 5
2 | Active caster module | 27 | 600 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 27 | 60 | 2016-12-01: 27
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 20 | 125 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 15 | 55 | 2016-11-01: 15
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 5 | 30 | 2016-12-01: 5
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 62.05 | 360 | 32.05 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 62.05 | 360 | 2016-11-01: 32.05; 2016-12-01: 30
| Total [h]: | 158.05 | 4237 | 82.05 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 125 | 110.575 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
| Total [CHF] | 19756.25 | 468506.275 | 10256.25 | 9500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## VISC
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 5.75 | 200 | 5.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 0 | 60
| Concept development | 5.75 | 40 | 2016-11-01: 5.75
| Sensor concept global and local | 0 | 40
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 0 | 60
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 5.75 | 4237 | 5.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 125 | 110.575 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
| Total [CHF] | 718.75 | 468506.275 | 718.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## KALA
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 20 | 200 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 5 | 60 | 2016-11-01: 5
| Concept development | 10 | 40 | 2016-11-01: 10
| Sensor concept global and local | 5 | 40 | 2016-11-01: 5
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 0 | 60
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 44 | 700 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 44 | 120 | 2016-11-01: 44
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 64 | 4237 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 105 | 110.575 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Total [CHF] | 6720 | 468506.275 | 6720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GRAU
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 20 | 200 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 5 | 60 | 2016-11-01: 5
| Concept development | 10 | 40 | 2016-11-01: 10
| Sensor concept global and local | 5 | 40 | 2016-11-01: 5
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 0 | 60
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 25 | 700 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 25 | 150 | 2016-11-01: 25
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 45 | 4237 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 165 | 110.575 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165
| Total [CHF] | 7425 | 468506.275 | 7425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## GEHM
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 25 | 200 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 5 | 60 | 2016-11-01: 5
| Concept development | 15 | 40 | 2016-11-01: 15
| Sensor concept global and local | 5 | 40 | 2016-11-01: 5
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 11 | 600 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 11 | 60 | 2016-12-01: 11
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 53 | 400 | 15 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 53 | 100 | 2016-11-01: 15; 2016-12-01: 38
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 3 | 360 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 3 | 360 | 2016-12-01: 3
| Total [h]: | 92 | 4237 | 40 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 105 | 110.575 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Total [CHF] | 9660 | 468506.275 | 4200 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DITF
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 0 | 60
| Concept development | 0 | 40
| Sensor concept global and local | 0 | 40
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 0 | 50
| Sensor concept | 0 | 60
| Construction and development | 0 | 200
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 0 | 55
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 0 | 4237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 105 | 110.575 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
| Total [CHF] | 0 | 468506.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## NIEE
hours [h]
WP Nr. | WP / Tasks | Total [h] | Estimated Total [h] | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01
1 | Requirements engineering / Concept | 20 | 200 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements engineering | 5 | 60 | 2016-11-01: 5
| Concept development | 10 | 40 | 2016-11-01: 10
| Sensor concept global and local | 5 | 40 | 2016-11-01: 5
| Sensor concept, sensor fusion, data flow | 0 | 15
| Recharging management | 0 | 15
| Power Management, Battery, Current distribution | 0 | 20
| Chair digitizing | 0 | 10
2 | Active caster module | 40 | 600 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drive concept, local power electronics | 20 | 50 | 2016-11-01: 20
| Sensor concept | 10 | 60 | 2016-11-01: 10
| Construction and development | 10 | 200 | 2016-11-01: 10
| Order of power electronics | 0 | 5
| Order, Production and montage | 0 | 75
| Integration, motor tests (with other drives) | 0 | 40
| Construction and Software development for simple test of all electronic components (2x drives, 3x Encoder, 2x motors, 1x slip ring) | 0 | 40
| Installation and commissioning the right drives and Construction | 0 | 130
3 | Algorithms and controllers | 4.5 | 125 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transformation algorithms | 4.5 | 55 | 2016-11-01: 4.5
| Exploration / development of a generic dynamic model | 0 | 30
| Algorithms for cartesian controllers | 0 | 30
| Verification / Experiments | 0 | 10
4 | First test only with baseframe | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and development the Baseframe | 0 | 150
| Order and Production | 0 | 10
| Mounting the drives | 0 | 40
| Commissioning and testing (not with the right electronics) | 0 | 50
5 | Robot software development | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Control-System for the drives | 0 | 150
| Sensors commissioning | 0 | 50
| People detection | 0 | 150
| Navigation, position detection, obstacle detection, | 0 | 150
| Control-System with sensors | 0 | 100
| Safety-System | 0 | 50
| Sequencer | 0 | 100
6 | Constructive postprocessing of the Chair | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction and manufacture of the prototype | 0 | 200
| Order and Production | 0 | 10
| Assembly and integration Automation module | 0 | 50
| Commissioning and testing | 0 | 40
7 | Small series production mechanik | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Order and produce of all mechanical parts | 0 | 10
| Montage | 0 | 45
| Commissioning and testing | 0 | 55
8 | Control hardware | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Main control: Evaluation, Procurement, Testing | 0 | 20
| EtherCAT | 0 | 100
| Servo Drives: Evaluation, Procurement, Testing | 0 | 15
| Sensor concept global and local | 0 | 90
| Security electronics: Evaluation, Procurement, Testing | 0 | 30
| PCBs and communication module development | 0 | 80
| Order and Production for Prototype | 0 | 50
| Hardware tests | 0 | 15
9 | Basic software development | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Robotics Library development, control system & safety system | 0 | 150
| Robotics Library development, sequencer | 0 | 70
| Robotics Library development, hardware abstraction layer | 0 | 120
| Test Cases | 0 | 100
| Operating system support (Kernel, QNX, …) | 0 | 120
| ROS interfaceing | 0 | 100
| Global Data Flow | 0 | 40
10 | Small series production electronic | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Extensive testing | 0 | 40
| Rework of the PCBs | 0 | 40
| Order and produce of all electronic parts | 0 | 30
| Hardware tests | 0 | 40
11 | Art performance development | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Concept development | 0 | 20
| Algorithms for demonstration | 0 | 150
| Simulation of the performance | 0 | 80
12 | Usability test, optimization | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Usability test, optimization, demonstration, exception tests | 0 | 42
13 | Project Management | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reporting, controlling and documetation | 0 | 360
| Total [h]: | 64.5 | 4237 | 64.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| CHF/h | 165 | 110.575 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165 | 165
| Total [CHF] | 10642.5 | 468506.275 | 10642.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0